Why Projects Go Wrong

- Lack of early equipment purchase.

- Lack of early equipment release.

- Using a non-specified manufacturer on bid day and then not being able to get that manufacturer approved after award of the contract.

- Missed items in estimate on bid day.

- Buying “erector sets” instead of preassembled packages.

- Subcontractors that cannot keep up with the project schedule.

- Incomplete scope of work.

- Late assignment of foreman to the job.

- Wrong foreman for the job.

- Over-the-counter purchasing of material.

- Crew mix is not monitored and adjusted.

- Wrong Project Manager for the job.

- Lack of Quality Assurance/Quality Control (QA/QC) on the job.

- Not taking responsibility for the job.

- Not asking for help when it is needed.

- Lack of attention to changed conditions.

- Not keeping track of the status and progress of the work.

- Estimate not taking job conditions into consideration.