## Sheet1
MONTHLY PROJECT STATUS REPORT
<MO/YR>
PROJECT NAME |  |  |  | PROJECT NO.
LOCATION |  |  |  | CUSTOMER
|  | CASH OUTLAY | POSTED COSTS |  | EST'D COST | F'CAST COST | LAST MONTH F'CAST COST
PURCHASED EQUIPMENT
MATERIAL
LABOR
SUBCONTRACT
OTHER DIRECT JOB COSTS
TOTALS |  | 0 | 0 |  | 0 | 0 | 0
TOTAL CASH RECEIVED |  |  | 0
TOTAL NET BILLED |  |  | 0
TOTAL GROSS BILLED |  |  | 0
CURRENT CONTRACT AMT |  |  | 0
1. ORIGINAL CONTRACT AMOUNT
2. CONFIRMED CHANGE ORDERS
| 3. CONTRACT AMOUNT TO DATE |  | 0
4. IN-PROCESS CHANGE ORDERS
| 5. EXPECTED MAIN CONTRACT |  | 0
6. MAIN CONTRACT GROSS BILLED
7. MAIN CONTRACT NET BILLED
8. MAIN CONTRACT PAYMENTS RECEIVED
ORIGINAL GROSS PROFIT
GROSS PROFIT 2 MO PRIOR
GROSS PROFIT 1 MO PRIOR
1. CURRENT ANTICIPATED GROSS PROFIT |  |  | 0
2. CURRENT MARK-UP % ON COST |  |  | %
3. EARNED GROSS PROFIT TO DATE |  |  | 0
4. EARNED GROSS PROFIT PRIOR YEAR |  |  | 0
5. EARNED GROSS PROFIT CURR YEAR |  |  | 0
6. UNABSORBED GROSS PROFIT |  |  | 0
7. NET BILLED LESS COST TO DATE |  |  | 0
8. OVER (UNDER) BILLED |  |  | 0
9. CASH OVERAGE (SHORTAGE) |  |  | 0
10. GROSS PROFIT % |  |  | %
% COMPLETE THIS REPORT |  |  | %
Instruction Sheet
Monthly Job Status Report
Cash Outlay
List actual cash expended for each of the 5 categories.
Posted Cost
List cost actually posted in the job cost accounting system.
Estimated Cost
Enter the cost from the original estimate plus any approved changes.
Forecast Cost
Enter the forecast final costs. This should include final costs on subcontractors, materials and equipment,
ODJC as well as a final labor forecast. Be sure to include costs for approved change orders as well as
change orders that are listed on Line 4 below.
Upper Section Lines 1-5
Line 1 | List amount of base contract.
Line 2 | List total dollar amount of approved changes.
Line 3 | Sum of Lines 1 and 2.
Line 4 | List total dollar value of changes that are in process, but are not listed in Line 2.
Line 5 | Sum of Lines 3 and 4.
Upper Section Lines 6-8
Line 6 | List Total Gross Billed.
Line 7 | List Gross Billings less retention held.
Line 8 | List total payments received.
Original Gross Profit
List the amount of the Original Target Gross Profit. This line will not change throughout the project.
Gross Profit 2 months prior
List amount from Line 1 in the lower section from two months prior. For example, if doing a status report for
March, list the gross profit from January.
Gross Profit 1 month prior
List the amount from Line 1 in the lower section from last month's report.
Lower Section Lines 1-10
Line 1 | Current Anticipated Gross Profit
Line 5 Expected contract amount less Total Forecast Cost
Line 2 | Current Mark-up % on Cost
Current Anticipated Gross Profit divided by Forecast Cost
Line 3 | Earned Gross Profit to Date
Current Anticipated Gross Profit times % complete this report
Line 4 | Earned Gross Profit Prior Year(s)
Enter the amount from Line 3 on the last report completed in the previous fiscal year
Line 5 | Earned Gross Profit Current Year
Line 3 less Line 4
Line 6 | Unabsorbed Gross Profit
Line 1 less Line 3
Line 7 | Net Billed less Cost to Date
Total Net Billings less Total Posted Costs
Line 8 | Over (Under) Billed
Total Gross Billed less Total Posted Costs less Earned Gross Profit to Date
Line 9 | Cash Overage (Shortage)
Total Cash Received less Total Cash Outlay
Line 10 | Gross Profit %
Current Anticipated Gross Profit divided by Expected Main Contract
% Complete this report
Total posted cost divided by total forecast cost.
What this report tells you:
This report will give you a quick financial snapshot of the project. In the Gross Profit Section, it will tell you if the gross profit is gaining or fading. It will tell you if you are over or under billed on the project. It will tell you if you are cash positive or negative on the project, and will give you the Gross Profit % on the project as well as the % complete. Remember the % complete is only a representation of the % complete financially, not the actual work done. It can be a valuable tool for quickly assessing where the project is. It is essential that this report be done as quickly after the end of the month as possible, after all of the costs and billings have been posted.