## Sheet1
ESTIMATING CHECKLIST
<Project Name>
Items to Check On
Air Handler and Air Conditioning Unit
Extended Warranty
Accessories
Vibration Isolators
Filters
Structural Supports or Bases
Assembled
Belt Guards
Curbs
Special Controls
Factory Start-Up
Exhaust Fans, Blowers, Gravity Vents
Backdraft Dampers
Vibration Isolators
Weatherproof covers
Inertia Bases
Curbs
Bird Screens
Belt Guards
Inlet Dampers
Structural Supports or Bases
Filters
Extra Filters
Frames
Wash Tanks
Gauges
Special Types
Air Distribution
Air Troffers
Terminal Units
Pressure Reducing Valves
Louvers
Fire Dampers (L.P. & H.P.)
Fire Damper Sleeves (L.P. & H.P.)
Hand Dampers
Automatic Dampers
Linears
Air Extractors
Operators for Terminal Units
Integrated Ceiling
Duct Access Doors (L.P. & H.P.)
Control Dampers
Computer Floor Registers
Special Duct Work Materials and Items
Materials: Aluminum
Materials: Black Iron
Materials: Stainless
PVC Coated
Duct board
Liner
Bracing
Access Doors Turning Vane
Welding
Screens
Hoods
Drain Pans
Rain Hoods or Eyebrows
Expanded Metal
Fire Damper Sleeves
Wall and Ceiling Escutcheons
Wall Packing or Caulking
Laid-Up Fiberglass
Ductmate or Special Connector
Plenums - Single Wall
Flex Duct (L.P. & H.P.)
Flex Connector
Prefab Pipe Fittings
Belt Guards
Stands, Platforms, Supports
Eliminators
Wall Sleeves
Grating
Angle Iron Frames for Fire Dampers
Oval Spiral Pipes and Fittings
Splitter Dampers
Welding or Auto Exhaust Systems
Blowers and Accessories
Flex Tubing (Special Materials)
Magnetic Adapters, Hoods, Boots, Cables
Supports
Ductwork and Pipe (Special Materials)
Dust Collectors
Collectors and Accessories
Ductwork and Piping (Special Materials)
Boots, Hoods
Flex Tubing (Special Materials)
Miscellaneous Equipment and Materials
Scrubbers, Assembled
Duct Mounted Coils
Plenum Mounted Coils
Manufactured Plenums
Paint Booths, Assembled
Evap. Coolers or Air Washers
Electric Heaters
Motors, Bases, Belts, Sheaves
Venting, Flues, Breeching
Furnaces and Heaters
Boilers
Dryers
Water Heaters
Special Equipment
Refrigerant Piping
Pipe and Fittings
Solenoid Valves
Filter Dryer
Oil Separator
Insulation
Welding Materials
Expansion Valves Sight Glass
Receiver-Relief Valve and Piping
Freon
ASME B 31.5 Requirements
Boilers
Insurance Certification
Concrete Base
Factory Start-Up
Atmospheric Vents
Special Controls
Chemical Treatment
Special Breeching
Chillers
Extended Warranty
Vibration Isolators
Concrete Base
Rupture Disk Vent
Motor Alignment
Factory Start-Up
Refrigerant
Motor Starters
Special Controls
Coils
Air Vents
Drain Valves
Flow Indicator
Flush and Clean
Special Test Connections
Compressors (HVAC)
Receivers
Dryers
Concrete Base
Factory Start-Up
Vibration Isolators
Motor Starters
Special Controls
Belt Guards
Special Cooling Controls
Drain Valves
Cooling Towers
Make-Up Water Control
Chemical Treatment
Rails
Ladders
Structural Support
Vibration Isolators
Balancing Valves
Motor Starters
Special Controls
Heat Exchangers
Air Vents
Special Controls
Structural Support
Humidifiers
Special Duct Connector
Special Controls
Incinerator
Permits
Special Controls
Factory Start-Up
Combustion Air
Special Code Requirements
Expansion Tanks
Structural Support
Drain Valves
Special Make-Up Controls
Radiation
Special Finish
Mounting
Access Panels
Special Controls
Tanks (HVAC)
ASME Rates
Concrete Base
Anchor Straps
Special Backfill
Structural Support
Type Material
Floor Drain
Outlet
Strainer
Body
Flashing
Grate
Special Variation
Pumps (HVAC)
Motor Alignment
Concrete Base
Vibration Isolators
Special Test Connection
Factory Start-Up
Motor Starters
Drain Pans
Special Controls
Gear Box, Reducers
Chemical Feeders
Extra Chemical
Special Testing
Factory Start-Up
Condensers
Extended Warranty
Factory Start-Up
Motor Starters
Vibration Isolators
Structural Steel Support
Fan and Coil
Air Vents
Extra Filters
Drain Valves
Flow Indicator
Flush and Clean
Special Test Connection
Motor Starter
Heaters
Special Traps
Air Vents
Special Flue
Structural Support
Motor Starters
Flush and Clean
Roof Drain
Outlet
Dome
Body
Sump Receiver
Under Deck Clamp
Extension Sleeve
Special Variation
Trench Drains
Outlet
Grate
Structural Support
Special Variation
Clean Outs
Outlet
Head
Type Finish Floor
Flashing Flange
Flashing
Material
Extra Length
Special Conditions
Grease Interceptors
Material
Special Mounting
Flow Control Valve
Capacity
Application
Special Access
Oil Interceptor
Material
Special Mounting
Special Flow Control
Capacity
Application
Special Access
Hair and Solid Interceptor
Material
Special Mounting
Special Sediment Basket
Capacity
Application
Wall Hydrant
Wall Thickness
Vacuum Breaker
Inlet
Anti-Freeze
Anti-Siphon
Type Finish
Special Variation
Water Meters
Permit and Fees
Application
Type
Cathodic Protection
Gas Meters
Permits and Fees
Application
Type
Cathodic Protection
Water Softeners
Concrete Base
Structural Support
Extra Fill Material
Brine Tank
Special Test Equipment
Factory Start-Up
ASME Rated
Domestic Hot Water Heaters
Fuel
ASME Rated
Storage Tank
Special Capacity
Special Controls
Type
Special Breeching
Factory Start-Up
Domestic Water House Pumps
Simplex
Duplex
Triplex
Motor Starters
Concrete Base
Structural Support
Special Controls
Vibration Isolator
Factory Start-Up
Domestic Central Drinking Water Chilled
Refrigerant
Make-Up Water Filter
Motor Starters
Special Mounting
Factory Start-Up
Vibration Isolator
Sewage Ejector
Simplex
Duplex
Motor Starters
Basin
Factory Start-Up
Pump Shaft Depth
Structural Support
Sump Pumps
Simplex
Duplex
Motor Starters
Basin
Factory Start-Up
Structural Support
Medical Air Compressor
Receivers
Dryers
Concrete Base
Factory Start-Up
Vibration Isolators
Motor Starters
Special Controls
Belt Guards
Special Cooling Controls
Drain Valves
Medical Vacuum Pump
Outlet Silencer
Concrete Base
Factory Start-Up
Vibration Isolator
Motor Starters
Special Controls
Belt or Shaft Guard
Special Cooling Control
Drain Valves
Receiver
Medical Gas Supply Equipment
Exterior
Interior
Special Enclosure
Special Ventilation
Manifold
Special Controls
Medical Gas Alarms & Outlets
PBX
Mounting Areas
Wall Material
Ceiling Material
Special Outlet Arrangement
Special Alarm Arrangement
Special Zone Valves
Medical Gas Installation Requirements
Training and Certification
Brazing Materials
Testing and Inspection
Tanks
ASME Rated
Concrete Base
Anchor Straps
Special Backfill
Structural Support
Special Access
Special Outlets
Type Material
Special Accessories
Vacuum Pump
Outlet Silencer
Concrete Base
Factory Start-Up
Vibration Isolators
Motor Starters
Special Controls
Belt Guards
Special Cooling Controls
Drain Valves
Whirlpool
Mounting
Special Rough-In
Mixing Valve
Overhead Carrier
Hospital Equipment and Fixtures
Autopsy Table
Emergency Bathtubs
Surgical Scrub-Up
Clinical Sink
Bedpan Sterilizer
Bedpan Washer
Glass Washer
Tray Washer
Instrument Sterilizer
Medicine Sink
Infant Bath
Body Bath
Leg Bath
Arm Bath
Sit Bath
Ice Maker
Plaster Skin
Emergency Shower
Emergency Eye and Face Wash
Fuse Hoods
Distiller
Dental Console
Nurses Station
Cup Sink
Mixing Valves for X-Ray
X-Ray Tray Sink
Kitchen Equipment
Broiler
Coffee Urn
Walk-In Cooler
Dishwasher
Food Warmer
Freezer
Fryer
Griddle
Ice Cube Maker
Range
Range Hood
Steamer
Pot Sink
Vegetable Sink
Disposal
Work Sink
Laundry Equipment
Washers
Dryers
Ironers
Lint Collector
Detention Equipment
Security Water Closet
Security Lavatory
Security Grilles
Swimming Pool Equipment
Pumps
Filters
Gutter System
Jets and Nozzles
Vacuum Equipment
Make-Up Water
Sewage Treatment Equipment
Water Treatment Equipment
Miscellaneous Equipment
Acid Neutralization Tank
Site Drainage and Utilities
Catch Basins
Manholes
Dewatering
Septic Tanks
Sewage Pump Station
Special Compaction
Spoil Removal
Tunnel Boring
Water Closets
Flush Valve Floor Mounted
Flush Valve Wall Mounted
Tank Floor Mounted
Concealed Flush Valve
Bedpan Washer
Bidet with Flush Valve
Special Carrier
Eastern Type
Handicapped
Urinals
Flush Valve Floor Mounted
Flush Valve Wall Mounted
Women's with Flush Valve
Trough
Concealed Flush Valve
Special Carrier
Handicapped
Lavatory
Wall Hung
Counter Top
Container
Corner
Legs and Bars
Steal Wall Plate
Special Carrier
Marble Vanity Top
Handicapped
Wash Fountains
Round
1/2 Round
Special Requirements
Bathtub
Cast Iron Recessed
Cast Iron Corner
Cast Iron Square
Steel Recessed
Plastic
Fiberglass
Handicapped
Showers
Stall, Complete
Base Only
2-Way Valve
Handicapped
Sinks
Service
Counter Top 1 Compartment
Counter Top 2 Compartment
Counter Top 3 Compartment
Mop
Floor
Special Trim
Lead Pan
Tub Protective Cover
Hose Spray
Foot Pedal
Lever Waste
Knee Action
Wrist Blade
Rigid Connections
Drinking Fountains
Wall Bubbler
Freeze-Proof Bubbler
Free Standing
Cuspidor
Floor Mounted
Wall Mounted
Handicapped
Fire Pumps
Simplex
Duplex
Motor Starters
Concrete Base
Structural Support
Special Controls
Vibration Isolators
Factory Start-Up
Jockey Pump
Fire Extinguishers
Recessed
Semi-Recessed
Surface Mount
Fire Department Connections
Wall Mounted
Sidewalk
Roof Mounted
Garage Equipment
Fuel Dispensing Pumps
Lubrication Dispensing Peales
Special Island Items
Auto and Truck Post Lift
Insulation
Duct
Refrigerant Piping
Drain Pans
Condensate Drains
Sanitary Waste
Storm
Domestic Hot and Cold Water
Chilled Water
Heating Water
Hot Water Heaters
Storage Tanks
Breeching
Miscellaneous
Contractors
Sheet Metal
Insulation Temperature Control
Air and Water - Test and Balance
Fire Protection
Electrical
Millwright
Painting
Utility
Excavation
Demolition
Core Drilling
Rigging and Hoisting
General Construction
Boilermaker
Structural Steel
Chemical Treatment
Waste Removal
Start-Up and Service
Instrumentation
Fabrication
Concrete Work
Tunneling And Drilling
Color Coding
Lawn Sprinkler
Fire Extinguisher System
Subcontractors
Moving and Hauling
Smoke Detection
Deodorizing System
Tank Erection
Engineering
Contract Labor
Breeching and Stack Erection
Fire Watch
Security
Traffic Control
Medical Gas Certification
Kitchen Equipment
Miscellaneous Subcontractors
Miscellaneous Items
Inserts
Block Outs and Sleeves
Inflation Factor
Service Contract
Sections 5, 7, 10, 13 of Specifications
Engineering
Owner Furnished Equipment
Cash Allowance
Space Allotments
Special Welding Certificate
Owner Instructions
Valve Tags
Material Handling
Punch List
Operation and Maintenance Manuals
Additional Project Drawings
Small Tools
Rental Equipment
Coffee Breaks
EEO Requirements
Liquidated Damages
Overtime
Photographs
Safety
Tenant Work
Traffic Control
Fire Watch
Electrical Controls and Power Wiring
Temperature Control Wiring
Insulation
Excavation
Concrete Pads, Foundations or Bases
Concrete Housekeeping Curbs
Concrete Thrust Blocks
Concrete Trench Drains
Rebar for Concrete
Cutting and Patching
Equipment Structural Support
Wood Bases and Platforms
Structural Support for Wall and Roof Penetrations
Mechanical Chase
Mechanical Painting
Mechanical Color Coding
Temporary
Temporary Heat
Temporary Power
Temporary Toilet Facilities
Temporary Fire Protection
Temporary Water
Temporary Water Meters
Temporary Phone
Temporary Gas
Temporary Fuel Oil
Temporary Fence
Temporary Barricades
Temporary Walks
Temporary Passageways
Temporary Signs
Utility Taps and Fees
Toilet Room Accessories
Toilet Room Partitions
Materials and Personnel Hoisting Facilities
Demolition
Cleanup
Storage Facilities
Office Facilities
Builders Risk Insurance
Bond
Mechanical Permits and Fees
Sales Tax
Extended Warranty
Access Panels
Cathodic Protection
Irrigation
Landscaping
Motor Starters
Gating
Access Doors
Heat Tape
Water Treatment
Welding Procedure Requirements
Welding Personnel Qualification Requirements