## Sheet1
PROJECT MANAGER'S SITE VISIT REPORT
Job No. |  | Job Name |  |  |  | Date
Job Foreman |  |  | Project Manager
GENERAL CONDITION OF JOB |  |  | YES | NO | EXPLANATION OF PROBLEMS AND ACTION TO BE TAKEN
1. | Job shack in order?
2. | Storage yard in order?
3. | Vehicles properly maintained?
4. | Material properly stored?
5. | Plans & specs in order?
6. | Shop drawings in order?
7. | As-builts current?
8. | Job filing in order?
SAFETY
9. | Hard hats being used?
Safety glasses being used?
10. | Accident reports current?
11. | Handrails provided?
12. | Fire extinguishers in proper condition?
13. | Gas boilers stored properly?
14. | Ditching & shoring in compliance?
15. | Safety posters properly posted?
16. | First aid kit properly maintained?
17. | Overall job compliance?
JOB SCHEDULE
18. | Are we delaying others?
19. | Are others delaying us?
20. | Has job schedule changed since last review?
CREW SIZE
21. | Is actual crew size as scheduled?
CHANGE ORDER STATUS
22. | Change Order Recap renewed?
23. | Are there any field COs in progress?
24. | Are there any field COs by others affecting us?
SUBCONTRACTOR'S PERFORMANCE
25. | Control sub performing properly?
26. | Insulation sub performing properly?
27. | Sheet metal sub performing properly?
28. | Sprinkler sub performing properly?
29. | _________ sub performing properly?
TEST REPORTS
30. | Test reports current?
31. | Test reports being signed by proper authority?
MATERIAL SHORTAGES/NEEDS
32. | Are there any items that have been ordered that haven't been received?
33. | Are you short material that hasn't been ordered?
EQUIPMENT
34. | Have you received approved submittal data on all equipment?
35. | Are scheduled equipment shipping dates compatible with job schedule?
36. | Has equipment been received complete?
37. | Has equipment been received undamaged?
CONSTRUCTION EQUIPMENT
38. | Is company owned equipment on the job needed?
39. | Is rental equipment on the job needed?
40. | Is there adequate equipment on the job?
LABOR REPORT
41. | Has labor been reviewed?
42. | Have variances been discussed?
43. | Has proper action been discussed with regard to negative variancies?
SPECIFIC JOB PROBLEMS
44. | Weather?
45. | Schedule?
46. | Coordination?
47. | Deliveries?
48. | Inspections?
49. | Changes?
50. | "Holds"?
JOB MORALE
51. | Is our job morale good?
52. | Is the GC job morale good?
PROJECT MANAGER'S GENERAL REMARKS