## Sheet1
<COMPANY NAME>
SHORT INTERVAL PLANNING CHECKLIST
Date:
Attendees:
| Dates of Action Plan |  | From: | To:
Check Item |  | Description | Comments
Review Master Schedule and Previous
Short Interval Plan and Results
Determine exact work to be accomplished
during next interval
Determine optimum crew sizes and
skill levels
Review subcontractor scheduling
Review with subcontractor availability
of workers, material and equipment to
meet schedule
Review prefabrication requirements
Review tools and special equipment
requirements
Review material deliveries
Review equipment deliveries
Review material handling procedures
Summarize plan and expected results