## Sheet1
PROJECT CLOSE-OUT REVIEW CHECKLIST/MINUTES
1. | PARTICIPANTS
PROJECT MANAGER
ESTIMATOR
JOB SUPERVISOR
2. | SAFETY
| A. | Were there any unique hazards that we need to consider on future jobs?
| B. | Were we required to have full-time safety personnel, fire watches, etc.?
| C. | Was the owner/client safety conscious?
| D. | Were there any major safety violations?
| E. | Did we have any serious accidents?
| F. | Was there an OSHA inspection?
| G. | Did we receive any citations from OSHA?
| H. | Are there any workers' compensation claims pending as a result of this job?
3. | REGARDING THE ORIGINAL ESTIMATE
| A. | Were the drawings complete and accurate?
| B. | What were the major assumptions used in estimating the job?
| C. | Were the assumptions correct?
| D. | What major variances occurred?
| E. | What caused them?
4. | COST/PROFITABILITY
| A. | How did final costs compare to estimated costs?
|  | 1. | General and administrative
|  | 2. | Material
|  | 3. | Purchased equipment
|  | 4. | Subcontracts
|  | 5. | Equipment rental
|  | 6. | Labor burden
|  | 7. | Labor
5. | DID WE FOLLOW THROUGH WITH OUR PREPLANNING GOALS?
| A. | Prefabrication
| B. | Materials handling
| C. | Shop drawings
| D. | Was the job adequately tooled and equipped?
| E. | Was office (Project Manager, superintendent) adequately supportive?
6. | HOW DID WE DO ON PAPERWORK?
| A. | From the office to the job
|  | 1. | Correspondence
|  | 2. | Purchase orders
|  | 3. | Subcontracts
|  | 4. | Meeting minutes
|  | 5. | Change order information
|  | 6. | Submittal data
|  | 7. | Roughing-in drawings
|  | 8. | Plans and specifications
|  | 9. | Foreman information/labor breakdown
|  | 10 | Shop drawings/spool sheets
|  | 11. | Labor reports
|  | 12. | Equipment reports
|  | 13. | Punch lists
|  | 14. | Requests for information
| B. | From the job to the office
|  | 1. | Time sheets
|  | 2. | Packing lists
|  | 3. | Daily reports
|  | 4. | Accident reports
|  | 5. | As-built drawings
|  | 6. | Warranty cards
|  | 7. | Installation instructions/erection prints
|  | 8. | Punch lists
7. | HOW WERE WE TREATED IN TERMS OF
| A. | Contract form/provisions
| B. | Payments
| C. | Coordination with other trades
| D. | Material handling facilities
| E. | Change orders
| F. | Backcharges
| G. | Scheduling
| H. | Punch list
| I. | Other considerations
8. | HOW WERE OUR RELATIONSHIPS WITH
| A. | The owner
| B. | Design professionals
| C. | The client
| D. | Our subcontractors
| E. | Other trades on the job
| F. | Suppliers and manufacturers
| G. | Who are the key players that we should remember?
1.
2.
3.
4.
5.
6.
9. | WERE THERE ANY CLAIMS OR MAJOR DISPUTES?
10. | HOW WERE THEY RESOLVED?
11. SCHEDULE
| A. | Who controlled the schedule?
| B. | Did the project follow the original schedule?
| C. | Did we do our own schedule?
| D. | Did we do regular updates?
12. | LABOR
| A. | How did the labor productivity compare to the estimate?
| B. | Was the labor breakdown helpful in tracking progress and productivity?
| C. | Should we have set the job up differently to facilitate labor tracking?
| D. | What factors influencing labor productivity should be considered in the future planning?
| E. | Did the breakdown have lost time codes?
| F. | Were they helpful in identifying problems?
| G. | Did we hit our targets for composition/average rate?
| H. | Was it difficult to staff the job? Where did the workers come from?
13. | MATERIAL
| A. | Were material deliveries timely?
| B. | Was the Project Manager's buyout accurate? Was much material ordered from the job?
| C. | Was the job supervisor able to track materials on the jobsite using POs from the Project Manager?
| D. | What vendors performed well?
| E. | What vendors performed poorly?
| F. | What new vendors should everyone know about?
14. | WHAT WERE THE THINGS WE DID THE BEST ON THIS JOB?
A.
B.
C.
D.
E.
F.
G.
H.
I.
J.
15. | WHAT MISTAKES DID WE MAKE? IF WE COULD DO THE JOB AGAIN, WHAT SHOULD WE DO DIFFERENTLY?
A.
B.
C.
D.
E.
F.
G.
H.
I.
J.
16. | HAVE APPROPRIATE "THANK YOU" LETTERS BEEN WRITTEN?