## Sheet1
SUBCONTRACT CHECKLIST
Instructions: This checklist is intended to serve as a reminder of the various provisions a subcontractor should review in a typical subcontract. You should complete the checklist for each subcontract that you review.
Name of Person Reviewing Subcontract:
Date of Subcontract Review:
Name of Project:
Name of General Contractor:
Be sure to review the subcontract for each of these items.
General Provisions |  |  | Notes
Review applicable State Contractor licensing law to
ascertain if subcontractors are required to be licensed.
Attain license number of subcontractor, if required in
the state where the work is to be performed.
Require the rights and benefits of the general
conditions to be passed through to the subcontractor.
Avoid waiving any rights allowed by law or the
general conditions.
Require that the laws of the state where the
project is located apply to the subcontract.
Require that the place for any suit or arbitration
be the location of the project.
Make attorneys' fees for breach of contract by
either party reciprocal or eliminate them.
Avoid expanded scope of work, including use of
terms such as "highest quality" or "highest standard."
Avoid unnecessary administrative requirements that were not part of the bidding documents such as daily workforce reports, the list of suppliers, schedules and copies of purchase orders.
Assure warranty begins upon substantial completion of subcontractor's work or when beneficial use by owner begins, whichever is earlier.
Payment |  |  | Notes
Assure payment dates are not more than seven days after payment is received from the owner.
Require monthly progress payments to include the value of material suitably stored on- or offsite plus work performed to date.
Assure retainage is consistent with owner-held retainage.
Retain entitlement to payment for work properly performed.
Retain right to stop work with appropriate notice when not paid.
Assure final payment is due upon completion of subcontractor's work - not completion of entire project.
Limit the requirement to provide monthly lien waivers from subcontractors and suppliers except when required by the bidding documents.
Insurance and Liability |  |  | Notes
Limit liability for negligent acts to only your negligence.
Limit damages you're responsible for to actual expenses incurred by the prime contractor. No incidental or consequential damages.
Limit prime contractor's ability to offset deductions against this subcontract only. Do not allow offset of insured claims.
Specify builder's risk coverage with the subcontractor as a beneficiary.
Require cost of performance and payment bonds to be paid by the prime contractor.
Avoid additional insured and other provisions requiring the subcontractor's insurance to be made "primary" to any insurance of the owner or contractor.
Avoid "hold harmless" clauses that require the subcontractor to incur the cost of the general contractor's OSHA fines.
Onsite Facilities and Schedule |  |  | Notes
Make performance schedules subject to timely availability and properly prepared work areas.
Specify temporary facilities to be provided by the prime contractor.
Require onsite location for debris at the expense of the prime contractor.
Require the general contractor to inspect and properly prepare all areas to receive the subcontractor's work before scheduling such work.
Changes, Delays, and Backcharges |  |  | Notes
Determine whether notices and times are achievable, and if not, change them.
Limit the contractor's delays to those a subcontractor normally experiences on a project of this size and type.
Retain right to additional time for delays that are beyond the subcontractor's reasonable control.
Assure that subcontractor's added cost for delays, acceleration and out-of-sequence work are addressed.
Require that change orders and extras be performed at your normal markup unless the bidding documents have established the markup.
Require advance written notice for backcharges.