<COMPANY NAME>

Turnover Meeting Agenda

<PROJECT NAME>

<PROJECT NUMBER>

□	Contract

Have we received a notice to proceed?				YES		NO

Have we received a contract?						YES		NO

Are there any potential problems or concerns with the contract
or its terms?								YES		NO

Who will our contract be with?

What type of contract? (circle one)

T&M-NTE			T&M			LUMP SUM

What type of project? (circle one)

Plan and Specification					Design-Build

Does our contract amount include any allowances?   		YES		NO

□	Plans and Specifications

Who is responsible for acquiring additional plans and specs?

How many sets do we need?

Are there any known engineering errors and omissions?		YES		NO

□	Review General Conditions

□	Addendums

Which addendum numbers have we received?

Which addendums affect our work?

Were any received after bid day?					YES		NO

□	Alternates

Were any alternates quoted with our bid?				YES		NO

Have any alternates been accepted?					YES		NO

□	Scope Letter

Review in great detail what is included, excluded and qualified.

□	Known Estimate Errors and Omissions

Identify all errors, omissions and problems with the estimate.

□	Labor

What is the estimated MCA labor factor?

How many labor hours (factored) are in the estimate?

What is the estimated average crew size?

What is the estimated average crew mix?

GF___AF___F___J___A5___A4___A3___A2___A1___Helper_____

What is the estimated peak crew size?

What is the estimated peak crew mix?

GF___AF___F___J___A5___A4___A3___A2___A1___Helper_____

Is overtime or shift work required?					YES		NO

Any other special labor concerns or considerations?    		YES		NO

Any special qualifications and certification required?   		YES		NO

□	Subcontractors

TRADE				COMPANY			   		CONTACT

Sheet Metal

Insulation

Temperature Controls

Testing and Balancing

Excavation

Hoisting/Rigging

Demolition

Prime Contractor

Concrete Cutting

Instrumentation

Are there any concerns or problems with any of the above subcontractors or the equipment and materials they are supplying?

YES		NO

□	Equipment Manufacturers and Material Suppliers

ITEM					COMPANY			     		CONTACT

Plumbing Fixtures

Plumbing Equipment

Drains/COs/Carriers

Hydronic Equipment

PVC Pipe/Fittings

Steel Pipe/Fittings

Cast Iron Pipe/Fittings

Copper Pipe/Fittings

Are there any concerns or problems with any of the above suppliers or the equipment and materials they are supplying?

YES		NO

□	Project Schedule

Start Date

Completion Date

Milestone Dates

Are we required to submit a schedule for our work?    		YES		NO

Any equipment/material items with a long lead time?  		YES		NO

Any equipment/material items requiring a rush submittal approval and rush delivery to the jobsite?

YES		NO

□	Identify Potential Piping Fabrication Opportunities

Were any portions of work estimated as fabricated? 			YES		NO

What portions of work should be/could be prefabricated?

□	Special Owner Safety Requirements and/or Hazards

Any specific safety issues or hazards related to this project?		YES		NO

Does this owner require any specific safety training for our
employees?								YES		NO

Does this owner require drug testing of our employees?		YES		NO

□	Special Tool and Equipment Requirements

Are there any special or “unusual” tools required to complete
this project (such as orbital welder, glass cutter, facing tool,
fusion machine, Vic Groover T-drill, etc.)?				YES		NO

□	Special Welding and Brazing Requirements

Are Welding and Brazing Procedure submittals required?		YES		NO

Are personnel qualification submittals required?			YES		NO

Any special welding procedures required

(such as X-ray testing, orbital welding, etc.)?			YES		NO

Any special materials?						YES		NO

Any special NDE (radiographs, etc)?					YES		NO

Any special certifications (med gas, etc)?				YES		NO

□	Miscellaneous